## Checklist
# | Phase | Owner | Milestone | Definition of Done | Est. Time | Status | Notes
1 | Pre-work | All | Read the guide | Every team member has read the Candidate Guide and the JD/Resume pack before 9:30 | Before day starts | Not Started
2 | 1 | All | Understand your role | Each person can explain what they're building and exactly what they're handing off / receiving | 15 min | Not Started
3 | 1 | All | Data contract locked | Shared JSON schema for skills/profile/match agreed and written down somewhere everyone can see | 30 min | Not Started
4 | 1 | All | Environment ready | Python env, React scaffold, and sample JD/resume files accessible to everyone; each person can run a hello-world for their piece | 15 min | Not Started
5 | 2 | JD Analytics | JD text extraction | Can load a PDF or DOCX JD and extract raw text | 30 min | Not Started
6 | 2 | JD Analytics | JD skill extraction | Produces a structured skill list in the agreed format for at least 3 of the 6 sample JDs | 60 min | Not Started
7 | 2 | Resume Parsing | Resume text extraction | Can load a PDF or DOCX resume and extract raw text | 30 min | Not Started
8 | 2 | Resume Parsing | Resume skill extraction | Produces a structured skill list in the agreed format for at least 2 of the 4 sample resumes | 60 min | Not Started
9 | 2 | Profile Builder | Profile form complete | Captures basic details, skills, hackathons/internships, certifications, preferred roles, and CV upload | 60 min | Not Started
10 | 2 | Profile Builder | Profile save/load + merge | A saved profile can be reloaded, and skills from Resume Parsing's output can be merged in | 45 min | Not Started
11 | 2 | Talent Check | Company skillset data loads | Can load a company's 12-skillset requirement snapshot | 30 min | Not Started
12 | 2 | Talent Check | Talent Check scoring | Comparing a saved profile to a selected company produces a readiness score and a per-skillset gap list | 60 min | Not Started
13 | 2 | Skill Matching | JD skill list loads | Can load one extracted JD skill list from JD Analytics' output | 20 min | Not Started
14 | 2 | Skill Matching | Skill match scoring | Computes and displays a match score with matched and missing skills for a profile against that JD | 70 min | Not Started
15 | 3 | All | Modules talk to each other | All 5 modules can read/write the shared JSON contract without errors when run back to back | 20 min | Not Started
16 | 3 | All | One shared screen | End-to-end flow works inside one shared app: pick a JD -> parse a resume -> build/update profile -> Talent Check -> Skill Match | 40 min | Not Started
17 | 3 | All | Two combos demoed | At least 2 of the 6 JD/role combinations run successfully end-to-end | 20 min | Not Started
18 | 3 | All | Bugs triaged | Known bugs/edge cases logged with a fix-if-time priority | 10 min | Not Started
19 | 4 | All | Walkthrough ready | 5-8 minute script or slides ready: problem, architecture, live demo, one challenge faced | 30 min | Not Started
20 | 4 | All | Demo rehearsed | Live demo rehearsed at least once, end to end, without a mentor's help | 15 min | Not Started

## Summary
RADIX Talent Match Hackathon — Progress Summary
Total milestones | 20
Done | 0
In Progress | 0
Blocked | 0
Not Started | 20
% Complete | 0%
By Phase
Pre-work | 1 | 0 | 0%
1 | 3 | 0 | 0%
2 | 10 | 0 | 0%
3 | 4 | 0 | 0%
4 | 2 | 0 | 0%
By Owner
Owner | Total | Done | % Done
All | 10 | 0 | 0%
JD Analytics | 2 | 0 | 0%
Resume Parsing | 2 | 0 | 0%
Profile Builder | 2 | 0 | 0%
Talent Check | 2 | 0 | 0%
Skill Matching | 2 | 0 | 0%